## Sheet1
# | Issue Reported | Issue/Feature | Arbitrage | Priority | Backlog | In Progress | QA | Production
1 |  | I |  | High |  |  | Apple IOS pops out the video
2 |  | I |  | Med |  |  | If left for a long screen goes black and long- it heygen timing out. Also the end session button is not greyed out
3 |  | I | webkit not getting the pauses correct. | Med
4 | butt-in support | F |  | Low
5 | scaling not correct for all screens | I |  | Low
6 |  | I |  | High |  |  |  | Sentence splitting incorrect for port St. Leica
7 |  | I |  | Med | Heygen and retell telltales in the HTML code
8 | When pressing the End session button, it doesn’t grey out | I |  | Low
9 |  | I |  | High |  |  | Mic timing on split sentences is wrong
10 | Buttons and mic don't scale | I |  | Low
11 |  | I |  | High |  |  | Funny chars still in the output from Stanza